## TPCA
PRE SCOPING TOTAL PROJECT COST ANALYSIS SUMMARY DESIGN-BID-BUILD
1
Project Infomration | SP : |  | Route |  | Analysis Summary Date:
| Cost Summary??: |  |  |  |  | Letting Date:
| Project Length: |  | Project Description:
DIVISION | GROUP | CATEGORY | DETAILS | Base Cost | Most Likely Cost | Pessimistic Cost | Expected Cost | The Most Cost
(Most risks)
Construction Letting | Construction Cost | [5 empty] | #N/A | #N/A
|  | Project Construction Costs |  |  | 0 | 0 | #REF! | #REF!
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
|  | Detours and Haul Roads | (Insert Details) |  |  |  | #N/A | #N/A
|  | Construction Traffic Mgmt | Extraordinary Reinforcement |  |  |  | #N/A | #N/A
|  |  | Incident Management |  |  |  | #N/A | #N/A
|  | Const Comm/Public Involvement |  |  |  |  | #N/A | #N/A
|  | Turn-Backs: Before |  |  |  |  | #N/A | #N/A
|  | Landscaping |  |  |  |  | #N/A | #N/A
|  | Environmental Mitigation |  |  |  |  | #N/A | #N/A
|  | Environmental Clean-Up |  |  |  |  | #N/A | #N/A
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
Construction Letting |  |  |  | 0 | 0 | 0 | #N/A | #N/A
Other Construction Total | [6 empty] | #N/A | #N/A
| Preconstruction Cost | [5 empty] | #N/A | #N/A
|  | Agreements |  |  |  |  | #N/A | #N/A
|  | Utilities | (Insert Details) |  |  |  | #N/A | #N/A
|  | Muncipal/Local Issues | (Insert Details) |  |  |  | #N/A | #N/A
|  | Railroad | (Insert Details) |  |  |  | #N/A | #N/A
|  | Environmental Mitigation |  |  |  |  | #N/A | #N/A
|  | Environmental Clean-Up |  |  |  |  | #N/A | #N/A
|  | Pre-Letting Traffic Mgmt | Enforcement and Incident Mgmt |  |  |  | #N/A | #N/A
| Preconstruction Cost |  |  | 0 | 0 | 0 | #N/A | #N/A
| Post Letting Cost | [5 empty] | #N/A | #N/A
|  | SA/Overruns |  |  |  |  | #N/A | #N/A
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
|  | Change Orders |  |  |  |  | #N/A | #N/A
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
|  | Incentives | (Insert Details) |  |  |  | #N/A | #N/A
|  | Construction Traffic Mgmt | Extraordinary Reinforcement |  |  |  | #N/A | #N/A
|  |  | Incident Management |  |  |  | #N/A | #N/A
|  | Detours and Haul Roads | (Insert Details) |  |  |  | #N/A | #N/A
| Post Letting Cost |  |  | 0 | 0 | 0 | #N/A | #N/A
| Post Construction Cost | [5 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
|  | Turn-Backs: After | (Insert Details) |  |  |  | #N/A | #N/A
|  | Landscaping |  |  |  |  | #N/A | #N/A
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
| Post Construction Cost |  |  | 0 | 0 | 0 | #N/A | #N/A
| Other Construction Elements |  |  | 0 | 0 | 0 | #N/A | #N/A
|  |  |  | 0 | 0 |  | #N/A | #N/A
CONSTRUCTION TOTAL | [6 empty] | #N/A | #N/A
Engineering | [6 empty] | #N/A | #N/A
| Pre-Letting | (12% of Construction Total) |  |  |  |  | #N/A | #N/A
|  | Environmental Studies |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  | Predesign/Scoping |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  | Detailed Design |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  | Traffic Management |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  | Comm/Public Involvement |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  | R/W Engineering |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
| Construction | (8% of Construction Total) |  |  |  |  | #N/A | #N/A
|  | Administration |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  | Traffic Management |  |  |  |  | #N/A | #N/A
|  |  | Internal |  |  |  | #N/A | #N/A
|  |  | External |  |  |  | #N/A | #N/A
|  |  |  | 0 | 0 |  | #N/A | #N/A
ENGINEERING TOTAL (20 % of Construction Total) |  |  |  | 0 |  | 0 | #N/A | #N/A
Right of Way | [6 empty] | #N/A | #N/A
| Standard Real Estate Purchase | [5 empty] | #N/A | #N/A
|  | Total Takes |  |  |  |  | #N/A | #N/A
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
|  | Partial Takes |  |  |  |  | #N/A | #N/A
| Relocation Costs | [5 empty] | #N/A | #N/A
|  | Residential |  |  |  |  | #N/A | #N/A
|  |  | (Insert Details) |  |  |  | #N/A | #N/A
|  |  |  | 0 | 0 |  | #N/A | #N/A
ROW TOTAL |  |  |  | 0 |  | 0 | #N/A | #N/A
Total Expected Cost |  |  |  | 0
Total the Most Cost with All Risks Considered | [5 empty] | 0
Total Project Cost Estimate | [6 empty] | #N/A | #N/A
|  |  | Cumulative Inflation Factor Used | #N/A
Mid-Point of Construction year
Estimator: |  |  |  | Approval By:
Project Manager: |  |  |  | Print Name:
Title:
Date:

## Proj. Construction Costs Risks
Risk No. | Risk Description | Status of Risk | Date Risk Identified | Contingency Type | Probability (P) | Linear/ Non-Linear | Contingency Amount | Contingency Amount | Impact (I) | Risk Weight | Overall Risk Rating |  |  |  |  | Risk Management Strategy | Response Action | Last Updated/Comments | Next Review Date
|  | Active |  | Time | 5=Very High (60-99%) | 5 =Very High |  |  | 16 =Very High | [6 empty] | AVOID
|  | Retired |  | Cost | 4=High (40-59%) | 4 =High | Linear |  | 8 =High |  |  | Score |  |  |  | MITIGATE
|  |  |  | Scope | 3=Med (20-39%) | 3 =Med | Nonlinear |  | 4 =Med |  |  | 1 | - | 6 | Low | ACCEPT
|  |  |  | Quality | 2=Low (10-19%) | 2 =Low |  |  | 2 =Low |  |  | 7 | - | 14 | Med | TRANSFER
[5 empty] | 1=Very Low (1-9%) | 1 =Very Low |  |  | 1 =Very Low |  |  | 15 | - | 80 | High
[6 empty] | Linear |  |  | Nonlinear
| MANUAL ENTRY | DROP DOWN | MANUAL ENTRY | DROP DOWN | DROP DOWN | DROP DOWN | MANUAL ENTRY | Hidden | DROP DOWN | AUTO (hidden) | AUTO |  |  |  |  | DROP DOWN | MANUAL ENTRY | MANUAL ENTRY | MANUAL ENTRY
1 | Risk Description | Active | Date | Time | 1=Very Low (1-9%) | Linear | Cost/Time Impact Value | Cost/Time Impact Value | 5 =Very High | 5 | Low |  |  |  |  | AVOID | Response Actions | Status Date & Comments | Date of Next Review
2 | [7 empty] | 0
3 | [7 empty] | 0
4 | [7 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39 | [7 empty] | 0
40 | [7 empty] | 0
41 | [7 empty] | 0
42 | [7 empty] | 0
43 | [7 empty] | 0
44 | [7 empty] | 0
45 | [7 empty] | 0
46 | [7 empty] | 0
47 | [7 empty] | 0
48 | [7 empty] | 0
49 | [7 empty] | 0
50 | [7 empty] | 0
[7 empty] | #DIV/0! | 0 |  | 5
0

## Inflation Factors
INFLATION ADJUSTMENTS
PROJECT COSTS - '10
| 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
FY 2011-14 STIP | 2011: 0.04; 2012: 0.04; 2013: 0.04; 2014: 0.04
FY 2015-20 |  |  |  |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04
CUMULATIVE | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802
| 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802
2007-12-11